## Sprint 1
Nombre del Proyecto:
Dueño del Proyecto
Gerente del Proyecto:
1
| Duración del Sprint | 10 |  |  | Esfuerzo | Faltante en los días siguientes…
| Tendencia calculada en los últimos | 10 | Días | Totales | 62 | 62 | 55 | 49 | 43 | 34 | 24 | 15 | 10 | 6
| Task rows | 4 | Done days | 9 |  | 62 | 55.8 | 49.6 | 43.4 | 37.2 | 31 | 24.8 | 18.6 | 12.4 | 6.2
| Warning! These are necessary |  | Trend |  |  | 62.8444 | 55.4111 | 47.9778 | 40.5444 | 33.1111 | 25.6778 | 18.2444 | 10.8111 | 3.3778
| template rows |  | Trend Days | 9 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
ID Tarea | Tarea | ID Historia | Responsable | Estado | Est. | 62.8444 1: 1; 55.4111 2: 2; 47.9778 3: 3; 40.5444 4: 4; 33.1111 5: 5; 25.6778 6: 6; 18.2444 7: 7; 10.8111 8: 8; 3.3778 9: 9; 3.3778 10: 10
1.1 | Tarea 1 | 1 | Luis | En Progreso | 15 | 62.8444 1: 15; 55.4111 2: 13; 47.9778 3: 11; 40.5444 4: 9; 33.1111 5: 7; 25.6778 6: 5; 18.2444 7: 3; 10.8111 8: 2; 3.3778 9: 1; 3.3778 10: 0
1.2 | Tarea 2 | 1 | Jorge | En Progreso | 17 | 62.8444 1: 17; 55.4111 2: 15; 47.9778 3: 14; 40.5444 4: 13; 33.1111 5: 11; 25.6778 6: 8; 18.2444 7: 5; 10.8111 8: 3; 3.3778 9: 2; 3.3778 10: 0
2.1 | Tarea 3 | 2 | Carolina | En Progreso | 12 | 62.8444 1: 12; 55.4111 2: 10; 47.9778 3: 9; 40.5444 4: 8; 33.1111 5: 6; 25.6778 6: 4; 18.2444 7: 3; 10.8111 8: 2; 3.3778 9: 1; 3.3778 10: 0
2.2 | Tarea 4 | 2 | Lucia | Por Hacer | 18 | 62.8444 1: 18; 55.4111 2: 17; 47.9778 3: 15; 40.5444 4: 13; 33.1111 5: 10; 25.6778 6: 7; 18.2444 7: 4; 10.8111 8: 3; 3.3778 9: 2; 3.3778 10: 0
Done
In Progress
To Do
Note on C16: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sprint 2
Nombre del Proyecto:
Dueño del Proyecto
Gerente del Proyecto:
2
| Duración del Sprint | 10 |  |  | Esfuerzo | Faltante en los días siguientes…
| Tendencia calculada en los últimos | 10 | Días | Totales | 62 | 62 | 55 | 49 | 43 | 34 | 24 | 15 | 10 | 6
| Task rows | 4 | Done days | 9 |  | 62 | 55.8 | 49.6 | 43.4 | 37.2 | 31 | 24.8 | 18.6 | 12.4 | 6.2
| Warning! These are necessary |  | Trend |  |  | 62.8444 | 55.4111 | 47.9778 | 40.5444 | 33.1111 | 25.6778 | 18.2444 | 10.8111 | 3.3778
| template rows |  | Trend Days | 9 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
ID Tarea | Tarea | ID Historia | Responsable | Estado | Est. | 62.8444 1: 1; 55.4111 2: 2; 47.9778 3: 3; 40.5444 4: 4; 33.1111 5: 5; 25.6778 6: 6; 18.2444 7: 7; 10.8111 8: 8; 3.3778 9: 9; 3.3778 10: 10
1.1 | Tarea 1 | 1 | Luis | Terminado | 15 | 62.8444 1: 15; 55.4111 2: 13; 47.9778 3: 11; 40.5444 4: 9; 33.1111 5: 7; 25.6778 6: 5; 18.2444 7: 3; 10.8111 8: 2; 3.3778 9: 1; 3.3778 10: 0
1.2 | Tarea 2 | 1 | Jorge | En Progreso | 17 | 62.8444 1: 17; 55.4111 2: 15; 47.9778 3: 14; 40.5444 4: 13; 33.1111 5: 11; 25.6778 6: 8; 18.2444 7: 5; 10.8111 8: 3; 3.3778 9: 2; 3.3778 10: 0
2.1 | Tarea 3 | 2 | Carolina | En Progreso | 12 | 62.8444 1: 12; 55.4111 2: 10; 47.9778 3: 9; 40.5444 4: 8; 33.1111 5: 6; 25.6778 6: 4; 18.2444 7: 3; 10.8111 8: 2; 3.3778 9: 1; 3.3778 10: 0
2.2 | Tarea 4 | 2 | Lucia | Por Hacer | 18 | 62.8444 1: 18; 55.4111 2: 17; 47.9778 3: 15; 40.5444 4: 13; 33.1111 5: 10; 25.6778 6: 7; 18.2444 7: 4; 10.8111 8: 3; 3.3778 9: 2; 3.3778 10: 0
Done
In Progress
To Do
Note on C16: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Plantilla Sprint
Nombre del Proyecto:
Dueño del Proyecto
Gerente del Proyecto:
1
| Duración del Sprint |  |  |  | Esfuerzo | Faltante en los días siguientes…
| Tendencia calculada en los últimos |  | Días | Totales | 0 | 0
| Task rows | 1 | Done days | 1 |  | 0
| Warning! These are necessary |  | Trend |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| template rows |  | Trend Days | 0 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
ID Tarea | Tarea | ID Historia | Responsable | Estado | Est. | bar: 1 to 25
Done
In Progress
To Do
Note on C16: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.